## Sheet1
Modules/Timeline | December |  |  |  | January |  |  |  | February |  |  |  | March
| W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1. Planning | bar: December W1 to December W2
1.1 Literature Review | bar: December W2 to December W3
1.2 Data Collection | bar: December W4 to January W1
1.3 Data Cleaning | bar: January W1
1.4 Data Pre-Processing | bar: January W1 to January W2
2. Website Development | bar: January W2 to January W3
2.1 User Interface | bar: January W3
2.2 Admin Interface | bar: January W4
2.3. School Interface | bar: February W1
3. AI Dev | bar: February W2 to February W3
3.1 Recommendation System | bar: February W3
3.2 Chatbot | bar: February W4
4. Database | bar: March W1 to March W2
4.1 Logical Design | bar: March W2 to March W3
4.2 Data Model | bar: March W3
5 Integration | bar: March W4